## Overview & TOC
Overview & TOC | [Project Name] | Customer Name / Logo
Purpose of this Document |  | Table of Contents
This document is the master project plan for the [Project Name] engagement. It provides a single, structured view of the project's objectives, scope, delivery approach, governance, and execution plan, from initiation through transition to business-as-usual. It is intended to: - Align all stakeholders on what will be delivered and how - Provide a clear execution roadmap across all project phases - Act as a single source of truth for scope, milestones, risks, issues, and decisions. |  | Sheet Name | Purpose
|  | Project Overview & TOC | High level project intro & Navigation
|  | Executive Summary | Executive summary
|  | Project KPIs | Project KPIs & success metrics
|  | Assumptions & Prerequisites | Contractual & delivery guardrails
|  | Dependencies | Internal & customer dependencies
|  | Technical Infrastructure | High-level infra overview
|  | Contacts | Project stakeholders and teams
|  | RACI | Responsibility clarity
|  | Issues | Issue log
Project objective |  | Risks | Risk Assessment & Management
The objective of this project is to [Project Objective]. |  | Decisions | Architecture & delivery approach
|  | Quality Assurance | Quality gates & acceptance
|  | Activities & Milestones | Your existing WBS
|  | Pre-sales readiness Checklists | Ensure key pre-sales items are done
|  | Post-sales readiness Checklists | Ensure key post-sales items are done
|  | Appendices & Change Log | Versioning & notes
Delivery Approach |  | Milestones & Key Dates
Phase | Purpose | Project Kick-off
Implementation start
Enrichment validated
Data Access & Segmentation live

## Executive Summary
Executive Summary | [Project Name] | Customer name / logo
Project Context
Add the project context here
Project Objectives
Add the project objectives here
In-Scope and Out-of-Scope Summary
Add the scope here
Success Criteria
Add success criteria here
Strategic Journey
Add the sequence of specific projects needed to accomplish the full required outcomes of the customer.
How to read this document
This project plan is organized into multiple sheets, each serving a specific purpose in tracking the project delivery. See the Overview & TOC sheet for navigation.
Navigation & Planning | Tracking & Governance | Reference & Support
• Overview & TOC - Start here for project introduction and navigation | • Issues - Log and track project issues | • Migration Scope - Detailed scope of migration items
• Executive Summary - High-level project context, objectives, and success criteria | • Risks - Identify, assess, and mitigate project risks | • Assumptions & Prereqs - Key assumptions and prerequisites
• Activities & Milestones - Detailed WBS with tasks, owners, dates, and effort | • Decisions - Record key project decisions | • Dependencies - Track internal and external dependencies
• RACI - Responsibility matrix for activities | • Quality Assurance - Quality gates and acceptance criteria | • Contacts - Key stakeholders and escalation paths

## Project KPIs
Project KPIs | [Project Name] |  | Customer name / Logo
The [Project Name] project KPIs track progress and outcomes across the wayfinder stages. Use these metrics to measure delivery health and stage completion.
Information Gathering for project sizing
Questions and information to gather about the customer organization, current practices and processes
Project Kick Off Date | 2026-01-01
Display Name | Unit Type | Value | Impact Area

## Assumptions & Prereqs
Assumptions & Prerequisites |  |  | [Project Name] |  |  |  | Customer name / Logo
This sheet captures the assumptions and prerequisites at the heart of this [Project Name] project.
Assumptions |  |  |  | Prerequisites
An assumption in a project context is a statement or condition that is believed to be true without proof, and upon which project planning and decisions are based. |  |  |  | A prerequisite in a project context is a condition, deliverable, or dependency that must be completed or in place before a specific task, phase, or the project itself can begin.
ID | Assumption | Impact if Invalid | Owner | ID | Prerequisite | Required By | Provided By | Status

## Dependencies
Dependencies |  | [Project Name] |  |  |  | Customer name / Logo
Dependencies
An external or internal factor, resource, or deliverable that a task, milestone, or the project relies upon, and which must be available or completed for work to proceed as planned.
Dependency ID | Description | Type (Internal/Customer/3rd Party) | Owner | Due By | Impact if Missed | Status

## Contacts
Contacts |  | [Project Name] |  |  | Customer name / Logo
Contacts
A contact in a project context is a key stakeholder, team member, or point of escalation whose role, responsibilities, and communication details are documented to ensure clear accountability and efficient collaboration throughout the project.
Name | Role | Team | Email address | Phone Number | Timezone

## RACI
RACI: [Project Name] |  |  |  |  | Customer name/logo
RACI
RACI is a responsibility assignment matrix that defines roles for each activity: Responsible (does the work), Accountable (owns the outcome), Consulted (provides input), and Informed (kept updated on progress).
Activity | Phase | EPM | Architect | Consultant | Customer | Sponsor

## Risks
Risks |  | [Project Name] | [10 empty] | Customer name/ logo
Risks
Here all identified risks are documented, tracked, and responses to said risks logged should they occur.
Risk ID | Open Date | Workstream | Topic | Description | Status | DT Owner | Plan Due Date | Probability | Impact | Risk Rating | Risk Factor | Response Type | Notes

## Activities & Milestones
WBS | Stage | Tasks | Description | Resources | Effort (days) | Owner | Start Date | End Date | Notes | Status

## Issues
Issues |  | [Project Name] | [11 empty] | Customer name / logo
Issues
The issue log is used to document, track, and manage problems or obstacles that arise during the project, ensuring they are assigned ownership, prioritized, and resolved in a timely manner to minimize impact on project delivery.
Issue ID | Open Date | Project Impact | Priority | Workstream | Topic | Description | Impact | DT Owner | Customer Owner | Due Date | Progress Notes | Status | DT Ticket # | DT Ticket Link

## Decisions
Decisions |  | [Project Name] | [8 empty] | Customer name/logo
Decisions
Here all decisions, considered options, decision makers, impacts and dates are documented.
Decision ID | Raised Date | Workstream | Topic | Description | DT Decision Maker | CUSTOMER decision maker | Options Considered | Decision | Impact | Decision Date | Status

## Quality Assurance
Quality Assurance |  | [Project Name] |  |  |  |  | Customer Name/Logo
Quality Assurance
For each project deliverable, list quality criteria, acceptance criteria, the people responsible for review and sign-off date.
Deliverable ID | Deliverable Name | Description | Quality criteria | DT Owner | CUSTOMER owner | Status | Sign-off date

## Pre-Sales Checklists
Commercial & Scope Readiness Checklist |  | Intake & Customer Alignment Checklist
Item | Status | Item | Status
Signed SOW or order form |  | Customer sponsor identified
Sales Hand-Over complete |  | Technical owner identified
Clear scope statement aligned to the Project type |  | Stakeholder list created
Defined Project name (e.g. "[Project Name]") |  | Communication plan agreed
Confirmed deliverables and success criteria |  | Kick-off meeting scheduled
Out-of-scope items documented |  | Customer expectations validated
Estimated timeline validated |  | Customer readiness questionnaire completed
Required customer resources identified |  | Customer environment overview collected (cloud providers, K8s, on-prem, tagging strategy)
Risks and assumptions captured
Dependencies documented (e.g. Cloud Access)

## Post-Sales Checklists
Delivery Readiness Checklist |  | Tooling & Automation Readiness Checklist
Item | Status | Item | Status
Engagement record created in Certinia |  | Intake form automation configured
Runbooks available |  | Quality gates or review checkpoints defined
Standard Project Plan loaded |  | Automation hooks identified
Appropriate progress tracker available |  | Reporting dashboards prepared
Naming standards applied |  | Document repository created (SharePoint, Confluence, etc.)
Versioning and Compliance rules confirmed |  | Project folder structure created
Risk & Dependency Validation Checklist |  | Internal Delivery Team Readiness Checklist
Item | Status | Item | Status
Known risks documented |  | Delivery lead assigned
Mitigation plans defined |  | Technical SMEs assigned
External dependencies identified (projects, teams) |  | Internal kick-off completed
Customer change freeze window reviewed |  | Roles & Responsibilities documented
Compliance and security rules captured |  | Delivery schedule reviewed
Required customer training or onboarding identified |  | Escalation paths defined
Internal communication channel created (Slack/Teams)
Customer Communication & Kickoff Checklist |  | Access & Environment Readiness Checklist
Item | Status | Item | Status
Kick-off deck prepared |  | Dynatrace tenant access granted
Agenda finalized |  | Customer VPN or SSO access approved
Introduction aligned |  | Cloud console access (AWS/Azure/GCP, etc.)
Project timeline drafted |  | Kubernetes cluster access
Success criteria restated |  | CI/CD access (Github, jenkins, etc)
Next steps defined |  | ServiceNow or ITSM access
Customer onboarding material sent |  | Log source access
Permissions validated (read/write where needed)

## Appendices & Change Log
Appendices & Changelog |  |  | [Project Name] |  |  | Customer name/logo
Changelog |  |  |  | Appendices
Document version | Date | Changed by | Comments | Name | Description | Link

## DATA
STEPS | Status
Understanding
Ingest
Observe
Analyze
Act